## Trusts (Acute & Community)
Lead Organisation | Site | Site Ownership | Project Name | Project Description | Strategic Objectives | Project Status | Total Scheme Value | 2025/26 Cost | Funding Source (and Value for each Source) | Status of Funding | Start Date | Completion Date | Status of Scheme | Project Governance
[5 empty] | Increased capacity / Maintenance-Quality-Compliance / Operational-BAU-Resilience / Efficiency / Transformation / Left Shift-Care Closer to Home / Elective Recovery-Performance Improvement / Net Zero-Climate Adaptation / Reducing Inequalities (Projects can deliver more than one of these) | [7 empty] | On Schedule Behind Schedule Significantly Off Track (< 6 months delay)
BHFT | Luton & Dunstable Hospital | BHFT Freehold | Redevelopment of Luton & Dunstable Site | This programme will deliver an Acute Services Block and New Ward Block consisting of: * Maternity services – delivery suite, 3 operating theatres, midwifery led birthing unit, triage, bereavement * NICU – intensive care, high dependency care, special care, transitional care * Critical Care – a 22-bed critical care floor * Surgical arrivals and recovery * Operating theatres – 8 new operating theatres, including two hybrid theatres, first stage recovery 2. * A maternity ward block with maternity wards (antenatal and postnatal) | Maintenance-Quality-Compliance | In delivery |  | £9.79m | PDC (Public Dividend Capital - Central NHS Funding) Trust Operational Capital Allocation | Funding secured - FBC approved by NHSE | 2022-01-01 | 2025-06-01 |  | Trust Board
BHFT | Bedford Health Village | BHFT Freehold | Gilbert Hitchcock House Reconfiguration | Transformation of part of Trust-owned Gilbert Hitchcock House building in Bedford into a Community Diagnostic Centre, due to complete in 2025. This will deliver therapy services, phlebotomy, and a number of diagnostic services including MRI, CT, ultrasound, x-ray and cardiology, amongst others. | Increased imaging capacity Maintenance-Quality-Compliance Elective Recovery | In delivery |  | £8.74m | STP Wave 3 CDC Funding System capital allocation | Funding secured - FBC approved by NHSE | 2024-02-01 | 2025-09-01 |  | Trust Board
BHFT | TBC |  | Luton Community Diagnostic Centre | Luton CDC business case development – awaiting NHSE agreement of fees to develop FBC. | Increased Imaging Capacity Elective Recovery | Scoping | £24.99m | £24.99m | TBC | TBC | TBC | TBC |  | Trust Board
BHFT | Bedford Hospital | BHFT Freehold | Same Day Emergency Care Unit (SDEC) |  | Increased Capacity Efficiency | In delivery |  | £6.20m | PDC and Trust | Approved | 2025-12-01 | 2025-09-01 |  | Trust Board
BHFT | L&D and Bedford Hospital sites | BHFT Freehold | BAU IT | Not agreed | Operational-BAU-Resilience |  |  | £5.91m | Operational Capital | Not yet secured |  |  |  | Trust Board
BHFT |  | BHFT Freehold | National Estates Safety | Not agreed | Maintenance-Quality-Compliance |  |  | £10.52m |  | Not yet secured
BHFT |  | BHFT Freehold | Physiological - Audiology | Equipment - clinical diagnostics |  |  | £0.14m | £0.14m | PDC - Constitutional Standards | Not yet secured
BHFT | L&D Hospital | BHFT Freehold | Chemo Unit | 6 additional chairs into unit - not agreed |  |  | £0.36m | £0.36m | PDC - Constitutional Standards | Not yet secured
BHFT | Bedford Hospital | BHFT Freehold | Outpatient Pharmacy | Creation of an outpatient pharmacy service to create the capacity for improve TTA dispensing (+ revenue saving) - not agreed |  |  |  | £1.8m | PDC - Constitutional Standards | Not yet secured
BHFT | Luton & Dunstable Hospital | BHFT Freehold | Audiology Booths | Creation of 2x audiology booths to address key strategic priority around paediatric audiology - not agreed |  |  |  | £0.14m | PDC - Constitutional Standards | Not yet secured
BHFT | TBC | TBC | Surgical Hub | New Build - Theatres & critical care - not agreed, system elective hub under discussion | Increased capacity Elective Recovery-Performance Improvement | In scoping | TBC | £1.0m | PDC - Elective Recovery 25/26 | Not yet secured
MKUH | TBC | TBC | Surgical Hub | New Build - Theatres & critical care - not agreed, system elective hub under discussion | Increased capacity Elective Recovery-Performance Improvement | In scoping | TBC | £1.0m | PDC - Consitutional Standards Elective Recovery 25/26 | Awaiting National NHS capital approval |  |  |  | Strategic Redevelopment Board
MKUH | Milton Keynes Hospital | MKUH Freehold | New Hospital Programme - Women's & Children's Hospital | The aim of the programme is to deliver a new Women’s and Children’s and Elective Surgery facility. The facility is being designed to include: * Elective surgery inpatient beds * Surgical outpatients * Maternity inpatient beds & delivery suite * Obstetric theatres * Maternity outpatients & ante-natal assessment * Neonatal unit * Paediatric inpatient beds * Paediatric outpatients * Refurbished Day Surgery Unit | Increased capacity | OBC in development | £284.78m | TBC | NHP | Funding for on-going design fees for 24/25 confired.Awaiitng formal ntoifictaion of deign team fees for 2025/26. MKUH also received confirmation that they are in wave 1 of the NHP | Not formally agreed, expect during 2027 | Not formally agreed, 3-4 years |  | Strategic Redevelopment Board
MKUH | Milton Keynes Hospital | MKUH Freehold | Multi-storey car park | Enabling scheme for NHP. Relocation and expansion of car parking capacity, including an additional multi-storey car park | Operational -BAU resilience | In delivery | £12.9m | £2.77m | PDC National funded by NHP - Signed MOU | National Funding secured | 2024-08-01 | 2025-06-01 |  | Strategic Redevelopment Board
MKUH | Milton Keynes Hospital | MKUH Freehold | Imaging Centre | Enabling scheme for NHP. New imaging centre | Operational -BAU resilience | In delivery | £24.99m | £16.70m | PDC National funded by NHP - Signed MOU | National Funding secured | 2024-08-01 | 2026-03-01 |  | Strategic Redevelopment Board
MKUH | Milton Keynes Hospital | MKUH Freehold | HV Supply | Enabling scheme for NHP. Additional HV supply | Operational -BAU resilience | In delivery | £3.3m | £2.99m | PDC National funded by NHP - Signed MOU | National Funding secured | 2024-03-01 | 2026-03-01 |  | Strategic Redevelopment Board
MKUH | Milton Keynes Hospital | MKUH Freehold | Oak House Ward | Oak Wards - 2 Storey building with 2 additional wards | Increased capacity | In delivery | £22.1m | £12.48m | Trust Operational Capital & Donated Funding £5m | Funding from MKUH | 2024-10-01 | Late spring 2026 |  | Strategic Redevelopment Board
MKUH | Milton Keynes Hospital | MKUH Freehold | Heat Decarbonisation | To switch connections to a new district heat network (DHN) that is coming to Milton Keynes for the provision of heat and hot water to the 3 main energy centres. It includes connection and infrastructure costs to site up to and including heat exchangers, Replacement of the energy centre ‘end-of-life’ boilers and 2 Combined Heat & Power plant (CHP) with connection to the heat exchangers and provision of new gas boilers (for resilience only) and Energy efficiency upgrades to air handling units (AHU) across the Trust, to improve thermal efficiency and energy use. | Net-Zero Climate Adaptation | In delivery | £14.7m | £11.64m | £12.9m Salix grant funding and £1.8m Trust Operational Capital | Salix Grant Funding approved | 2025-01-01 | 2027-03-01 |  | Strategic Redevelopment Board
MKUH | Milton Keynes Hospital | MKUH Freehold | Low carbon heating project | Low carbon heating project in Hospital Phase2 Estate .Air Source Heat Pumps to replace the Combined Heat and Power boilers, Localised Steam Generation, Air Handling Units with Heat Recovery and Electronically Commutated Motors, Domestic Hot Water Calorifiers, Cascading Air Source and High Temperature Water Source Heat Pumps and Ancillaries | Net-Zero Climate Adaptation | Completed | £6.8m |  | £4.8m Salix grant funding and £2m Trust Operational Capital | Salix Grant Funding approved | 2023-08-01 | 2025-03-01 |  | Strategic Redevelopment Board
MKUH | Milton Keynes Hospital | MKUH Freehold | Additional Outpatient Rooms | Creation of an additional 15 OP rooms and a minor elective procedure room | Performance Improvement | In scoping | £1.2m | £1.2m | PDC - Consitutional Standards Elective Recovery 25/26 | Awaiting National NHS capital approval |  | During 25/26 |  | Strategic Redevelopment Board
MKUH | Milton Keynes Hospital | MKUH Freehold | Diagnostic Equipment | Various equipment across diagnostic services | Performance Improvement | In scoping | £0.79m | £0.79m | PDC - Constitutional Standards Diagnostics 25/26 | Awaiting National NHS capital approval |  | During 25/26 |  | Strategic Redevelopment Board
MKUH | Milton Keynes Hospital | MKUH Freehold | ED reconfiguration | Reconfigutaion of ED to improve flow put | Performance Improvement | In scoping | 0.57m | 0.57m | PDC - Constitutional Standards UEC 25/26 | Awaiting National NHS capital approval |  | During 25/26 |  | Strategic Redevelopment Board
MKUH | Milton Keynes Hospital | MKUH Freehold | Estates Safety | Windows, theatre ventilation and roofing | Maintenance-Quality-Compliance Operational-BAU-Resilience | In scoping | £4.94m | £4.94m | PDC - Estates Safety 25/26 | Awaiting National NHS capital approval |  | During 25/26 |  | Strategic Redevelopment Board
Cambridgeshire Community Services NHST | Redgrave Gardens | Chiltern Academy Trust | Reconfiguration of Redgrave Gardens, Luton | Change of ownership wil generate revenue cost pressure. Reconfiguration will reduce footprint rquired and thereby mitigate cost increases as far as possible. | Operational-BAU-Resilience | Potential reconfiguration proposal being developed. Will then require costing. Awaiting LL valuation to understand the cost pressure and so determine the VfM of the scheme. | £0.35m |  | tba | tbc | tbc | tbc |  | Trust Board
ELFT | Bedford Health Village | House of Industry - under long head lease to NHS PS | Bedford Mental Health Inpatient Unit | Planning to deliver a circa 60-bed mental health inpatient unit on the Bedford Health Village site | Care Closer to Home | Case for Change developed. Complexity around potential funding arrangements.
ELFT (Specialist Services) | TBC | TBC | Learning Disability & Autism Capital | Open market purchase of residential accommodation for 3 complex patients with Learning Disability and/or Autism | Efficiency / Care Closer to Home | Bid submission to NHSE end of April 2025 |  |  | National LDA Capital | Not yet secured |  |  |  | Specialist Commissioning
East London NHS Foundation Trust |  |  | Ward improvements | Reopening & Adapting Existing Acute Beds (9 additional bedrooms) at Calnwood and Oakley Court | Reducing Out of Area Placement | Agreed/recommended to progress to SFBC | £0.89m |  |  | Not yet secured
East London NHS Foundation Trust | Cedar House |  | Crisis House | Creation of a Crisis House (8 beds) and Step Down Unit (4 beds) at Kelvin Grove |  | Agreed/recommended to progress to SFBC | £1.0m |  |  | Not yet secured
East London NHS Foundation Trust |  |  | Step Down Facilities | Community Rehab Service |  | Agreed/recommended to progress to SFBC | £2.0m |  |  | Not yet secured
ELFT | Cedar House BHV | NHSE | Cedar HDU | Cedar House @ Bedford Health Village - re-purposing to become a MH High Dependency Unit (HDU) | Reducing Out of Area Placement | ACTIVE | £2.0m | £2.0m | NHSE | Not yet secured | TBC | TBC
ELFT | Charter House | ELFT leasehold | Charter House Lease Works | Charter House - Lease Works | Asset & Backlog Management | ACTIVE | £0.41m | £0.41m | CDEL | Approved | TBC | TBC
ELFT | Charter House | ELFT leasehold | Charter House MEP Works | Charter House - MEP Works | Asset & Backlog Management | ACTIVE | £0.32m | £0.32m | CDEL | Approved | TBC | TBC
ELFT | Onyx ward, Calnwood | ELFT freehold | Onyx bedroom doors | Onyx ward, Calnwood - KINGSWAY Safety Door upgrade to bedrooms | Mental Health Safety & Security Improvement Plan | ACTIVE | £0.26m | £0.26m | CDEL | Approved | TBC | TBC
ELFT | Townsend Court | ELFT freehold | Townend Ct bedroom doors | Townsend Court - KINGSWAY Safety Door upgrades to bedrooms | Mental Health Safety & Security Improvement Plan | ACTIVE | £0.25m | £0.25m | CDEL | Approved | TBC | TBC
NHSPS | Bedford Health Village | House of Industry - under long head lease to NHS PS | Additional Parking | Creation of additional parking to the rear of Shires House | Operational-BAU-Resilience | In Scoping | 0.2 | 0 | TBC | NHS PS Disposal Recycling | TBC | 2026 |  | NHS PS IAP

## Primary Care
Lead Organisation | Site | Site Ownership | Project Name | Project Description | Strategic Objectives | Project Status | Total Scheme Value | 2025/26 Cost | Funding Source (and Value for each Source) | Status of Funding | Start Date | Completion Date | Status of Scheme | Project Governance
[5 empty] | Increased capacity / Maintenance-Quality-Compliance / Operational-BAU-Resilience / Efficiency / Transformation / Left Shift-Care Closer to Home / Elective Recovery-Performance Improvement / Net Zero-Climate Adaptation / Reducing Inequalities (Projects can deliver more than one of these) | [7 empty] | On Schedule Behind Schedule Significantly Off Track (< 6 months delay)
SCHEMES PRIORITISED IN JANUARY 2023
BLMK ICB and BBC | TBC | TBC | Reprovision of King Street Surgery | Relocation of 3 premises (1 GP Practice) into a primary care Hub in Kempston | Increased capacity / Efficiency / Transformation / Reducing Inequalities | Scoping | TBC | 0 | TBC | Not yet secured | TBC | TBC |  | Bedford Borough Strategic Estates Board; PCCAC
BLMK ICB | S106 site in Biddenham | Private ownership | Biddenham New Surgery | Move of De Parys Bromham branch and Linden Road Bromham branch to new build facility | Increased capacity / Efficiency / Transformation / Reducing Inequalities | In planning | £5.9m | 0 | Private investment (ICB revenue investment) | Not yet secured | TBC | TBC |  | PCCAC
BLMK ICB and CBC | Kings Grove, Cranfield | Private ownership, transferring to CBC | Cranfield New Surgery | New purpose-built compliant GP surgery, future proofed with extension capability as significant local housing developments reach completion. Expectation of full range of services & full-time opening to local patients | Increased capacity / Efficiency / Transformation / Reducing Inequalities | In delivery | £2.50m | Not known | S106 & Private Investment | Paid |  | Autumn 2025 |  | PCCAC
BLMK ICB and BBC | Great Barford Lower School | BBC | Great Barford new surgery | Redevelopment of former school site to enable relocation of this exceptionally constrained practice & support them to absorb current/new housing growth | Increased capacity / Efficiency / Transformation / Reducing Inequalities | In planning | £3.4m | 0 | BBC | Secured in principle | TBC | TBC |  | Bedford Borough Strategic Estates Board; PCCAC
MKCC and BLMK ICB | New site in East MK Expansion Area | MKCC | East MK Expansion Area / Elverby Centre | New build health/community facility in expansion area. MK Council managing the delivery. | Responding to population growth / Care Closer to Home | In delivery | £8.06m | Not known | £7.5m HIF Funding £0.3m NHS £0.26m MKCC | Funding secured - construction underway | 2023-09-01 | 2025-09-01 |  | PCCAC
Practice - Westfield Road | Westfield Road Surgery | Practice-owned | Westfield Road Extension | Proposal to extend surgery utilising S106 funding secured in relation to Newton Leys housing development. | Increased Capacity | Planning | £1.71m | TBC - seed funding for fees | S106 Funding | Secured in principle | TBC | TBC |  | PCCAC
CBC and BLMK ICB | Steppingley Extra Care Facility | CBC | Flitwick Extra Care | Plans to construct two clinical rooms plus ancillary space within Flitwick Extra Care Housing for use by nearby GP practice (S106 funded). | Increased Capacity / Transformation | In delivery | £0.14m | Not known | S106 | Funding secured - construction underway | TBC | 2025-07-01 |  | PCCAC
VOID UTILISATION PROJECT
BLMK ICB and NHS PS | Leighton Buzzard Health Centre | NHS PS | Leighton Buzazrd Helth Centre (repurpose new void space) | Conversion of admin space into 6 additional clinical rooms | Increased Capacity / Transformation | In planning |  |  | NHS PS Capital | Funding secured | 2025-01-01 | 2025-06-01 |  | PCCAC
BLMK ICB and NHS PS | Queens Park Health Centre | NHS PS | Queens Park Health Centre (re-purpose void space) | Conversion of void space in the Health Centre for primary care use | Increased Capacity / Transformation | In planning |  |  | NHS PS Capital | Funding secured | 2025-01-01 | 2025-06-01 |  | PCCAC
BLMK ICB | Liverpool Road Health Centre | NHS PS | Liverpool Road Health Centre (re-purpose void space) | Proposal to re-purpose void space in the Health Centre for primary care use | Increased Capacity / Transformation / Reducing Inequalities | In scoping | TBC | 0 | NHS PS Capital | Not yet secured | TBC | 2025 |  | PCCAC
BLMK ICB | Sandy Health Centre | NHS PS | Sandy Health Centre (re-purpose void space) | Proposal to re-purpose void space in the Health Centre for primary care use | Increased Capacity | In planning | Not known | Not known | NHS PS Capital | Funding secured | TBC | TBC |  | PCCAC
BLMK ICB | Gooseberry Hill Health Centre | NHS PS | Gooseberry Hill Health Centre (re-purpose void space) | Proposal to re-purpose void space in the Health Centre for primary care use | Increased Capacity | In scoping | Not known | Not known | NHS PS Capital | Funding secured | TBC | TBC |  | PCCAC
BLMK ICB | Houghton Regis Health Centre | NHS PS | Houghton Regis Health Centre (re-purpose void space) | Proposal to re-purpose void space in the Health Centre for primary care use | Increased Capacity / Transformation / Reducing Inequalities | In scoping | TBC | TBC | TBC | Not yet secured | TBC | 2025 |  | PCCAC
S106 FUNDED PROJECTS
BLMK ICB | Shefford Health Centre | Private ownership NHS PS are headlease holder | Shefford Health Centre - reconfiguration of practice area | Two -phase proposal to re-configure space in the practice space to increase clinical capacity | Increased Capacity | In scoping | £0.68m | £0.68m | S106 Funding | Business case approval in progress |  | 2025 |  | PCCAC
Practice - Lower Stondon Surgery | Lower Stondon Surgery | Practice-owned | Lower Stondon Extension | Plan to increase and reconfigure the space within the building to increase clinical capacity - 2 Phase Project | Increased Capacity | In planning | £0.96m | TBC | S106 Funding | Secured in principle |  | TBC |  | PCCAC
Practice - Caddington Surgery | Caddington Surgery | Practice-owned | Caddington Extension | Proposal to extend building to increase clapacity | Increased Capacity | In scoping | £0.47m | TBC | S106 Funding | Secured in principle |  | TBC |  | PCCAC
Practice - Greensand Surgery | Potton Surgery | Practice-owned | Potton Surgery Improvements | Proposal to reconfigure the surgery to create an additional consulting room | Increased Capacity | In scoping | TBC | TBC | S106 Funding | Not yet secured |  | TBC |  | PCCAC
Practice - Greensand Surgery | Gamlingay Surgery | Practice-owned | Gamlingay Surgery Improvements | Proposal to reconfigure the surgery to create an additional remote consultation room and staff welfare area | Increased Capacity | In scoping | TBC | TBC | S106 Funding | Not yet secured |  | TBC |  | PCCAC
Practice - Saffron Road Health Centre | Langford Surgery | Practice-owned | Langford Surgery Improvements | Discussions with practice to encourage them to use S106 near expiry date | Increased Capacity | In scoping | TBC | TBC | S106 Funding | Not yet secured |  | TBC |  | PCCAC
OTHER PROJECTS
BLMK ICB |  |  | Wixams Feasibility | Exploratory discussions with Bedford Borough and Central Bedfordshire Councils about affordable options for bringing forward a new surgery as part of Wixams town centre development, including exploration of a temporary facility | Increased Capacity / Transformation | In scoping | £4.5m | 0 | Not yet known | Not yet secured |  | TBC |  | PCCAC
BLMK ICB and NHS PS |  |  | Luton Town Centre Surgery & UTC relocation - feasibility | Feasibility work to consider potential relocation to an alternative facility in Luton | Operational-BAU-Resilience | In scoping | TBC | 0 | Not yet known | Not yet secured |  | TBC |  | PCCAC
BLMK ICB and LBC |  |  | Wenlock Street | Proposal to bring premises back into use for primary care | Increased Capacity / Transformation | In scoping | TBC | 0 | Not yet known | Not yet secured |  | TBC |  | PCCAC
BBC and BLMK ICB |  |  | Wootton Surgery Relocation | Feasibility study led by Bedford Borough Council | Increased Capacity / Operational-BAU-Resilience | In scoping | TBC | 0 | BBC | Not yet secured |  | TBC |  | Bedford Borough Strategic Estates Board; PCCAC
Practice - Neville Road |  |  | Neville Road Surgery extension | Practice-led project to extend the premises | Increased Capacity | In delivery | £0.06m | £0.06m | ICB Capital - GP IT only | Not yet secured |  | 2025-07-01 |  | Practice / PCCAC
BLMK ICB |  |  | Newport Pagnell Surgery extension/ reconfiguration | Potential S106 funded project to increase capacity | Operational-BAU-Resilience | In scoping | TBC | TBC | S106 Funding | Not yet secured |  | 2025/26 |  | PCCAC
PROPOSED UTILISATION & MODERNISATION FUNDING PROJECTS - SUBJECT TO DUE DILIGENCE
Practice | Lea Vale Medical Group - Whipperley Medical Centre branch | Leasehold | Whipperley UMF Project | Conversion of side part of reception area into two additional clinical rooms | Increased clinical capacity | In scoping | £0.04m | £0.04m | Utilisation & Modernisation Fund | Secured in principle | 2025-10-01 | 2025-12-01 |  | PCCAC
Practice | Pastures Way Surgery | Freehold | Pastures Way UMF Project | 1. To convert three existing toilets and part of entrance foyer into an extra clinical room. 2. Create a single disabled toilet to replace the three existing toilets using part of the records area. 3. Move the server to an opposite wall in the secretaries' room, enabling this room to be merged with the HCA room in order to utilise this room for extra clinical capacity/diagnostics | Increased clinical capacity | In scoping | £0.12m | £0.12m | Utilisation & Modernisation Fund | Secured in principle | 2025-10-01 | 2025-12-01 |  | PCCAC
Practice | Malzeard Road Surgery | Freehold | Malzeard Road UMF Project | Creation of triage hub room by upgrading a small room on Ground Floor, releasing a clinical room for face-to-face appointments. Potential additional scheme to convert loft into admin space, enabling relocation of admin team and expansion of waiting area - enabling higher throughput of patients and therefore additional appointments. | Increased clinical capacity | In scoping | £0.12m | £0.12m | Utilisation & Modernisation Fund | Secured in principle | 2025-10-01 | 2026-02-01 |  | PCCAC
Practice | Woodland Avenue Practice | Freehold | Woodland Avenue UMF Project | Development of multifunctional areas that can serve more then one purpose within existing practice space, enhancing the practice experience for both staff and patients. Creation of 2 new clinical spaces along with redesign of a number of existing spaces to ensure they are accessible and multifunctional. One of the new rooms will re-purpose the existing nursing room into 2 clinical spaces for phlebotomy/ecg/simple nursing along with a clinical space to be used by Duty GP for adhoc examinations. The second will provide a comfortable and welcoming space for MH triage and assessment by our aligned ELFT MHLW - moving away from the more cold appearance of clinical rooms. This room can also be used for palliative care family discussions as required. Installion of a platform lift making our first floor accessible to patients with mobility needs; thus further expanding capacity to provide care for pts. | Increased clinical capacity | In scoping | £0.21m | £0.21m | Utilisation & Modernisation Fund | Secured in principle | 2025-10-01 | 2025-12-01 |  | PCCAC
Practice | Stopsley Village Surgery | Freehold | Stopsley Village UMF Project | 1) Internal changes in the admin room upstairs to create x2 additional clinical rooms and create additional working space in the loft area for relocating admin staff from current admin room. 2) To create partition in the reception area to create x1 additional clinical room and use the rest of space as reception. 3) Moving of IT cabinet (currently upstairs) to the loft space to create additional toilet for patients on the first floor. | Increased clinical capacity | In scoping | £0.19m | £0.19m | Utilisation & Modernisation Fund | Secured in principle | 2025-10-01 | 2025-12-01 |  | PCCAC
Practice | Neville Road | Freehold | Neville Road UMF Project | Turning admin / reception rooms into clinical capacity to offer 35-40 more appointments per day. The space will facillitate a remote clinical offer enabling the ARRS GP to provide more clinical capacity, will also allow GPs to conduct remote booking, total triage and virtual consultation. Additionally, the health and wellbeing coaches can utilize the space to offer face to face consultations . Furthermore it will allow dedicated spaces for pharmacists, social prescribers and health coaches to support patients more effectively . | Increased clinical capacity | In scoping | £0.03m | £0.03m | Utilisation & Modernisation Fund | Secured in principle | 2025-10-01 | 2025-12-01 |  | PCCAC
Practice | King Street Surgery | Freehold | King Street UMF Project | Conversion of now redundant dispensary to consulting room | Increased clinical capacity | In scoping | £0.01m | £0.01m | Utilisation & Modernisation Fund | Secured in principle | 2025-09-01 | 2025-10-01 |  | PCCAC
Practice | Putnoe Medical Centre | NHSPS | Putnoe UMF Project | Dividing a large consulting room (previous seminar room) room into 2 separate consulting rooms. | Increased clinical capacity | In scoping | £0.93m | £0.93m | Utilisation & Modernisation Fund | Secured in principle | 2025-10-01 | 2025-12-01 |  | PCCAC
Practice | Lea Vale Medical Group - Bushmead Medical Centre | Leasehold | Bushmead UMF Project | Re-design the entire internal area, generating an extra 5 clinical rooms, 46,800 appointments per year. | Increased clinical capacity | In scoping | £0.31m | £0.31m | Utilisation & Modernisation Fund | Secured in principle | 2025-10-01 | 2025-01-01 |  | PCCAC
Practice | Elstow Medical Centre | Leasehold | Elstow UMF Project | Ground floor room conversation from admin room/small kitchen to clinical room. Along with vacant space converted to admin office on second floor. | Increased clinical capacity | In scoping | £0.94m | £0.94m | Utilisation & Modernisation Fund | Secured in principle | 2025-10-01 | 2025-12-01 |  | PCCAC
Practice | Churchfield Health Centre - Castle Medical Group and Larkside Practice | Leasehold | Churchfield UMF Project | Both practices to add 2 clinical rooms each in current waiting room area utilising the wasted space in waiting room. Spilt shared room in half to make 2 separate rooms to offer room space for sessions for other services so that the patients in this neighbourhood don't have to travel to the L&D Hospital. Possibly CAMHS, Talking Therapies, ICaSH Sexual Health Clinic, Parkinson's Disease Nurse, Mental Health Link Worker, Dietician, Phlebotomy, Podiatry, Continence Service, Diagnostics for all the neighbourhood practices, ie Scanning. Requires a sound-proof partition wall, wipeable flooring and IT Connection to make this room patient suitable. | Increased clinical capacity | In scoping | £0.37m | £0.37m | Utilisation & Modernisation Fund | Secured in principle | 2025-10-01 | 2025-02-01 |  | PCCAC
Practice | Leagrave Surgery | Leasehold | Leagrave UMF Project | 1) Conversion of Records Storage Room to an Additional Clinical Consulting Room 2) Conversion of Side Examination Area (Room 6) to a Telephone Consultation/ Clinical Triage Room. | Increased clinical capacity | In scoping | £0.04m | £0.04m | Utilisation & Modernisation Fund | Secured in principle | 2025-10-01 | 2025-12-01 |  | PCCAC
Practice | Barton Hills Surgery | Leasehold | Barton Hills UMF Project | Division of one large nurses' room into two separate spaces to accommodate additional clinical staff. Additionally, a small attached examination room will be converted into another functional clinical room, further increasing space for patient consultations and treatments. | Increased clinical capacity | In scoping | £0.06m | £0.06m | Utilisation & Modernisation Fund | Secured in principle | 2025-10-01 | 2025-12-01 |  | PCCAC

## Completed Schemes
Lead Organisation | Site | Site Ownership | Project Name | Project Description | Strategic Objectives | Project Status | Total Scheme Value | 2024/25 Cost | 2025/26 Cost | Funding Source (and Value for each Source) | Status of Funding | Start Date | Completion Date | Status of Scheme | Project Governance
[5 empty] | Increased capacity / Maintenance-Quality-Compliance / Operational-BAU-Resilience / Efficiency / Transformation / Left Shift-Care Closer to Home / Elective Recovery-Performance Improvement / Net Zero-Climate Adaptation / Reducing Inequalities (Projects can deliver more than one of these) | [8 empty] | On Schedule Behind Schedule Significantly Off Track (< 6 months delay)
MKUH | Milton Keynes Hospital | MKUH Freehold | Radiotherapy Centre | The opening of a new Radiotherapy Centre at MKUH in partnership with Oxford University Hospitals | Increased capacity Left Shift-Care Closer to Home Performance Improvement | Completed | £15m |  |  | £5.7m from MKUH Council remainder Trust Funded | Fully Funded | 2022-11-01 | 2024-03-01 | Complete | Strategic Redevelopment Board
MKUH | Lloyd Court (Central MK) | Private Landlord | CDC - Lloyd Court | Delivery of a new Community Diagnostic Centre at Lloyd Court in Central Milton Keynes. To be operational by the end of 2024. | Increased capacity Elective Recovery | Completed | £9.6m | £0.6m |  | STP Wave 3 CDC Funding | Signed MOU | 2023-10-01 | 2024-10-01 | Complete | Strategic Redevelopment Board
Cambridgeshire Community Services NHST | Child Development Centre, Kempston | Bedford Borough Council | Reconfiguration of Child Development Centre, Kempston | Conversion of former admin space to clinical to increase utilisation for clinical delivery following creation of admin base at Woburn Court | Operational-BAU-Resilience | ACTIVE | £0.11m | £0.11m |  | Trust Operational Capital | Paid | 2024-04-01 | Aug'2024 | Complete | Completed
ELFT | Rush court | Private landlord | Rush Court Bedford -Installation of Pinpoint sytem | Install a staff alarm system (Pinpoint), to support staff in a CAMHS outpatient setting | Operational-BAU-Resilience | ACTIVE | £0.089m | £0.089m |  | CDEL £89,000 |  | Nov/Dec 2024 | 2025-01-01 | Complete
ELFT | Crystal ward | ELFT | Crystal Ward Luton -Installation of bedroom access control | Installation of an access control system for patient bedrooms. Patient to wear wristbands for access | Increased capacity / Maintenance-Quality-Compliance / Operational-BAU-Resilience | ACTIVE | £0.06m | £0.06m |  | PDC £60,000 |  | 7th October 24 | October 2024 | Complete
ELFT | Luton Centre for Mental Health | ELFT Freehold | HBPoS Improvements (Coral Ward) | Improved visibility of section 136 room and provision of stepdown room with en-suite facilities. | Operational-BAU-Resilience/ Increased capacity | ACTIVE | £0.85m spread over 2 years. | £0.6m |  | 24/25 PDC £418,00 + CDEL £181,000 |  | 28th May 2024 | 5th November 2024 | Complete
ELFT | Bedford Health Village | House of Industry - under long head lease to NHS PS | Fountains Court - Accessibility Improvement | Internal improvements to make the ward accessible (access control) | Reducing Inequalities | ACTIVE | £0.044m | £0.044m |  | CDEL - £44,000 |  | November/December 2024 | 2025-01-01 | Complete
SCHEMES PRIORITISED IN JANUARY 2023
BLMK ICB | Enhanced Services Centre, Bedford Health Village | CHP | North Bedford Programme / De Parys Group reprovision | The De Parys Group relocation to Enhanced Services Centre (ESC) as part of an integrated Hub on the Bedford Health Village site | Increased capacity / Efficiency / Transformation / Reducing Inequalities | In delivery | 4.01m |  |  | £3.80m STP Wave 3 £0.21m ICB Capital | Paid |  | 11th November 2024 | Complete | Hub Programme Board - ICB and BHFT; PCCAC
BLMK ICB | Kempston Health Centre, Halsey Road | NHS PS | Cater Street branch surgery reprovision (Kempston Health Centre) | Reconfiguration works at Kempston Health Centre to enable relocation of Cater Street Surgery | BAU-Resilience | Complete | £0.46m | £0.46m |  | ICB BAU Capital | Funding secured - construction complete |  | 2024-09-30 | Complete | PCCAC
BLMK ICB | Ampthil Health Centre | NHS PS | Ampthill Health Centre reconfiguration (Greensand Surgery, Oliver Street Surgery, Hillton PCN & Leavale PCN) | Relocation of ELFT within Ampthill Health Centre building to free up rooms to be converted into additional clinical rooms for severely constrained Greensand Surgery, Oliver Street Surgery, Hillton PCN & Leavale PCN | Increased capacity | Complete | £0.11m | £0.11m |  | S106 Funding | Paid |  | 2024-04-01 | Complete | PCCAC
BLMK ICB | London Road Health Centre | NHS PS | London Road surgery - additional rooms | Project for practice to take on additional rooms in current premises to mitigate severe space constraints (and avoid liability for void costs) following ELFT vacating premises | Increased Capacity | Complete | 0.0015 | 0.0015 |  | NHS PS | Paid |  | 2024-08-01 | Complete | PCCAC
BLMK ICB | London Road Health Centre | NHS PS | East Bedford PCN | Proposal for PCN to take on one void admin room and one clinic room in London Rd Health Centre for the PCN | Increased Capacity | Planning | £0.002m | £0.002m |  | NHS PS | Funding secured | 2024-11-01 | 2024-11-01 | Complete | PCCAC
BLMK ICB | Water Eaton Health Centre | NHS PS | Water Eaton | Proposal for practice to formally take on “void” space in the Health Centre for their exclusive use. | Increased Capacity | Complete | 0 | 0 |  | Revenue only - net-saving against void costs | N/A |  | 2024-04-01 | Complete | PCCAC
BLMK ICB and CBC | Grove View Hub | CBC | Grove View Hub - PCN Space | Conversion of records room into dedicated PCN space within Grove View Hub | Increased Capacity / Transformation | In delivery | 0.04 | 0.04 |  | S106 | Funding secured |  | 2024-11-01 | Complete | PCCAC
OTHER PRIMARY CARE PROJECTS
BLMK ICB | Leighton Buzzard Health Centre | NHS PS | Leighton Linslade Health Connections - extra clinical space | Scheme for PCN in Leighton Buzzard to take on a further 2.7 clinical rooms at Bassett Road Health Centre | Increased Capacity / Transformation | Complete | Not known | Not known |  | NHS PS Capital | Funding secured - construction underway |  | 2024-04-01 | Complete | PCCAC
BLMK ICB | Linden Road Surgery |  | Linden Road Extra Clinical Room | Proposal to reconfigure the surgery to create an additional consulting room | Increased Capacity | Complete | £0.08m | £0.08m |  | ICB Capital | Secured in principle |  | 2025-03-01 |  | PCCAC